## Sheet1
Journal
Date | What is done | What needs to be done
2014-12-04 | Project Proposal | Start First Grading period requirements
2014-12-05 | Created basic outline | Find images
2014-12-08 | Images found and edited | Create Homepage template
2014-12-09 | Homepage template created | Create Genre template pages
12/9/2014-12/12/2014 | Genre template pages created | Finish Homepage
12/18/2014-12/19/2014 | Worked on Homepage | Finish Homepage
1/12/2015-1/14/2015 | Finshed Homepage | Start Second Grading period requirements
1/12/2015-1/14/2015 | Created basic artist template | Create artist pages for the first three genres
1/14/2015-3/20/2015 | Created artist pages for first three genres | Create artist pages for the last three genres
3/20/2015-4/28/2015 | Created artist pages for last three genres | Finish requirements needed
2015-05-04 | Finsihed requirements needed | Test the webpage
5/4/2015-5/7/2015 | Webpage tested and approved